## Sheet1
June 2020 Work Plan
S/N | Task | Description | Priority | Deliverable/Expected Result | Responsible Party(ies) | Timeline
[6 empty] | Start Date | End Date
1 | Forecast Not reporting some shut-in Limiting constraints | Identified that the Shut-in Limiting Constraint was not reported on the result table for cases where the Cumulative production value is equal to the UR | Must have | Forecast should start reporting shut-in limiting constraints for Cum production value equal to UR | Ebuka, Fidel, Ndubuisi | Jun-08-2020 | Jun-09-2020
2 | Responsiveness of module selection in Table view | The responsiveness of the module selection and what appears on the forecast result table view needs to be synchronised. For example, switching to view 2P Forecast Results most times retains the Forecast results from 1P Table while 2P has been activated. | Must have |  | Ndubuisi |  | Jun-10-2020 | MSCW Definition
3 | Inconsistent Availability-Decline rate calculation | Observed that the Availability declined gas rate calculation for Availability scenarios of gas modules is not consistent with what is expected as seen for the Availability declined oil rates for oil modules | Must have |  | Ebuka, Ndubuisi |  | Jun-11-2020 | Must have | Extremely important updates, features that are mandatory for client engagement
4 | Export button not working | Observed that the Export button on the Result Export Settings does not work | Must have |  | Ndubuisi |  | Jun-13-2020 | Should have | Important updates, features that are not vital, but add significant value for client engagement
5 | Wrong Running App name | The application crashed at a point and the dialog box error as shown below carries a ' WRFM' label instead of a ' SEPAL BFS' label. | Could have |  | Ndubuisi |  |  | Could have | Nice to have updates, features that will have a small impact of left out
6 | Plateau Period over shooting | On running the forecast for the PECON deck, it was observed that the plateau period of 0.5 which should translate to 6 months was not respected. The forecast results show the plateau period for 7 months contrary to the expected 6 months. | Could have |  | Ndubuisi |  |  | Won't have | Updates, features that are not a priority for this specific time frame
7 | Change Flow station header | Flow station table header that carries ‘compressor availability’ accessed by double-clicking on the flow station icon from the network diagram should be changed to ‘pump availability’. | Must have |  | Ndubuisi
8 |  |  | Won't have
9 | Show network diagram to fit screen size | It was observed that On generating the network diagram, the network diagram is expected to zoom to fit the window by default. However, on trying to zoom to fit the window the diagram is skewed. The ' zoom to fit' view can be adjusted to cover the full size of the view and be made default view | Should have |  | Ndubuisi
10 | Expose forecast result table to property Grid | The forecast result table should be exposed to the property explorer to help manage things like the number of decimal places forecast results are being reported. Also, the header of the forecast results should have the forecast scenario being reported appended to the asset name | Must have |  | Ndubuisi
11 | Revert back to original state of imported deck | Input deck modification of a module is via the optimisation log view are being saved and used to run the forecast. The challenge is that users cannot revert back to the original values from the input deck once modified, a functionality that will either enable users to revert back to the original input deck imported, export modified input deck as a new input deck or save modification made on the input deck via the visualization log view as a vintage of the original deck needs to be implemented to maintain input deck integrity and evolution. | Should have |  | Ndubuisi
12 | If 1p fails a constraint forecast should run for 2p and 3p | If the cumulative volume produced is greater than the 1P UR but less than the 2P UR scenario. the forecast should run without outputting 1P forecast results. Currently, the module is removed totally once the cumulative volume produced is equal to or more than at least one of the 1P, 2P or 3P UR values. | Must have |  | Ebuka, Ndubuisi
13 | BSW, GOR, and WC not affecting forecast termination date | Observed that the forecast termination date is not affected by increasing or decreasing the initial or abandonment BSW and or GOR values because the trending of WC or GOR is a function of UR. | Won't have
14 | Combo Chart | Implementation of combo charts for example, a combo plot of stacked bar chart for liquid and oil rate at facility level and a line chart of the Facilty's Liquid Capacity all on the same chart | Should have |  | Ndubuisi, Visualization team
15 | Add new variables for plotting | Facility Gas Demand, Gas Capacity and Liquid Capacity should be added to the list of plot variables in the Forecast Result Chart. | Must have |  | Ndubuisi, Ebuka
16 | Remove new algorithm option | Removing the New Algorithm combo box under the Activate Full Solver in the Options menu | Must have |  | Ndubuisi
17 | Change the position of Gas demand | The Business Demand combo option should be moved to the Forecast Condition ribbon group of the Forecast and Optimisation tab. The combo name should be " Gas Demand" and on hovering, the message should be "Allow Gas Demand Constraint"-Checked by default | Must have |  | Ndubuisi, Fidel
18
19
20
21
22
23
24
25
26
27
28
29
30